## Sheet1
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
1. File corruption | unable to write and update files | Low | High | Devs | Try your best to recover files using older commits | maintain protocol of branching
2. Computer breakdown | loss of saved files | Low | High | Devs | try to resolve the issue and recover any lost files | make sure to commit small changes so you always have the updated files.
3. compatability error | compatibility issues with software | Low | High | Devs | try and find altervative software which is compatible. | make sure the software is compatible before starting project
4. Sensitive info | leaks of sensitive informations like passwords etc. | Low | Medium | Devs | try to reset passwords. | setup two-factor authentication to beef up security
5. Time | tight deadline | High | High | Devs | prioritise the minium to get the application working | make sure to plan ahead and use time wisely.